Revenue Operations Command Center
AsterPeak Software — Revenue Operations Capstone
Prepared by Tyler Medders

Business Context:

AsterPeak Software is a fictional B2B SaaS company that provides workflow automation software to small and mid-sized businesses. The company has grown rapidly to approximately $15–20 million in annual recurring revenue and employs roughly 100 people across Sales, Marketing, Customer Success, Finance, Product, and Operations.

AsterPeak generates pipeline through inbound marketing, outbound prospecting, webinars and events, partner referrals, and direct sales activity. Salesforce serves as the company’s primary CRM, while HubSpot supports marketing lead generation and campaign activity. As the company has grown, its go-to-market processes, CRM governance, reporting standards, and commercial workflows have become increasingly inconsistent.

Project Problem:

Leadership no longer fully trusts the company’s CRM data or revenue reporting. Sales, Marketing, Finance, and Customer Success rely on the same underlying systems, but inconsistent data entry, unclear lifecycle definitions, stale opportunities, routing issues, and inconsistent discounting have created uncertainty around pipeline quality, forecasting, and sales performance.

The Revenue Operations function has been asked to assess the current state, identify operational and data-quality issues, determine where performance is being lost, and design a more reliable operating framework for CRM governance, pipeline management, reporting, and commercial approvals.

Project Objectives:

The objective of this project is to evaluate AsterPeak Software’s revenue operations environment, identify weaknesses in CRM data quality, lead management, pipeline governance, forecasting, and commercial workflows, and design a more reliable operating framework that supports scalable growth.

Specific objectives include:

• Assess CRM data quality and identify incomplete, inconsistent, stale, or improperly assigned records.
• Evaluate lead routing, lifecycle progression, and source performance to identify process breakdowns and conversion opportunities.
• Analyze opportunity pipeline health, sales velocity, win rates, deal size, and stage progression across segments, territories, and sales representatives.
• Evaluate forecast reliability by comparing opportunity stages, close dates, probability assumptions, and historical outcomes.
• Review discounting and deal-approval patterns to identify commercial risk and opportunities for stronger governance.
• Develop improved CRM standards, lifecycle definitions, lead-routing logic, pipeline-management rules, and approval workflows.
• Build reporting and dashboard solutions that provide leadership and sales teams with clearer operational visibility.
• Present findings and recommendations in a concise executive-level case study.

Stakeholders:

Executive Sponsor: VP of Revenue
Primary Stakeholders: Sales Leadership, Revenue Operations, Marketing Operations, Finance, Customer Success
Operational Users: Account Executives, Sales Development Representatives, Sales Managers
Supporting Teams: Product, Legal, and Business Systems

Scope:

In Scope
• CRM data quality and governance across leads, accounts, contacts, opportunities, and sales activities.
• Lead lifecycle definitions, qualification criteria, ownership, routing logic, and handoff processes.
• Opportunity pipeline health, stage progression, close-date management, sales velocity, win/loss analysis, and forecast reliability.
• Sales performance analysis by representative, segment, territory, lead source, and deal characteristics.
• Discounting behavior, pricing consistency, and commercial approval requirements.
• Revenue operations reporting, KPI definition, dashboard design, and executive visibility.
• Process documentation, CRM standards, and recommendations for improved operating discipline.

Out of Scope
• Product development and engineering decisions.
• Detailed customer-success retention or churn modeling beyond information needed to understand revenue operations.
• Full financial planning, accounting, or company-wide budgeting.
• Production deployment into a live company environment.
• Real customer or confidential company data; all project data will be synthetic and created specifically for this case study.

Key Business Questions:

• How reliable is AsterPeak’s CRM data, and which data-quality issues most directly affect reporting, routing, forecasting, and sales execution?
• Which lead sources generate the highest-quality pipeline, conversion rates, and closed-won revenue?
• Are leads being assigned to the correct owners and territories, and where are routing or handoff failures occurring?
• Where do leads and opportunities most frequently stall or drop out of the funnel?
• How do conversion rate, win rate, average deal size, and sales-cycle length vary by segment, territory, source, and sales representative?
• Which opportunities appear stale, overstated, or unlikely to close based on stage age, activity history, close dates, and other pipeline signals?
• How accurate and trustworthy is the current revenue forecast?
• Which sales representatives or teams show meaningful differences in pipeline quality, conversion efficiency, activity levels, or deal progression?
• How are discounts being used across deals, and are larger discounts associated with better win rates, lower revenue quality, or approval risk?
• Which deal characteristics should trigger additional commercial, Finance, or management approval?
• Which CRM fields, lifecycle definitions, stage criteria, and required processes should be standardized to improve data quality and operating discipline?
• What KPIs and dashboards should executives, sales managers, and frontline sellers use to monitor revenue performance and identify problems earlier?
• What operational changes would most improve pipeline visibility, forecast reliability, sales efficiency, and cross-functional coordination?

Deliverables:

• Project Charter: Formal definition of the business problem, project scope, stakeholders, objectives, key business questions, technology stack, and success criteria.
• Synthetic CRM Dataset: A realistic multi-table B2B SaaS dataset containing leads, accounts, contacts, opportunities, sales activities, products, territories, and sales users, including intentionally embedded data-quality and process issues.
• Data Dictionary: Documentation defining every field, table, relationship, accepted values, and intended business meaning across the CRM dataset.
• CRM Data Quality Audit: Assessment of missing, inconsistent, duplicate, stale, misrouted, or otherwise unreliable records, including quantified findings and recommended governance controls.
• PostgreSQL Database: Relational database environment containing the project dataset with appropriate table relationships and keys.
• SQL Analysis Portfolio: Documented SQL queries using joins, aggregations, CASE logic, CTEs, date functions, and window functions to analyze pipeline health, conversion, performance, forecasting, activity, and commercial trends.
• Excel Analysis Workbook: Supporting audit, reconciliation, validation, and ad hoc operational analysis using formulas, lookups, pivot tables, and structured data review.
• Power BI Revenue Operations Dashboard: Interactive reporting environment covering executive KPIs, funnel performance, pipeline health, sales performance, lead-source effectiveness, forecasting, and commercial trends.
• Salesforce Configuration: Trailhead Playground demonstrating selected CRM improvements such as custom fields, validation rules, reports, dashboards, lifecycle standards, and opportunity governance.
• Lead Lifecycle and Routing Framework: Defined lead stages, qualification criteria, ownership rules, handoff expectations, service-level expectations, and exception handling.
• Opportunity and Pipeline Governance Framework: Standardized stage definitions, entry and exit criteria, required fields, close-date rules, next-step expectations, and stale-pipeline management procedures.
• Deal Desk and Discount Approval Workflow: Commercial approval framework defining standard discounts, escalation thresholds, exception criteria, required approvers, and supporting documentation.
• Process Maps and SOP Documentation: Visual workflows and written procedures documenting the redesigned revenue operations processes.
• Executive Recommendations: Prioritized recommendations based on project findings, including expected business impact, implementation considerations, and proposed success metrics.
• Executive Presentation: Concise presentation summarizing the business problem, analysis, key findings, recommendations, and proposed operating model.
• GitHub Repository: Organized repository containing SQL, documentation, data definitions, project assets, and selected technical deliverables suitable for employer review.
• Final Case Study: Polished end-to-end written case study explaining the problem, methodology, analysis, findings, solutions, and lessons learned.
• Portfolio Website: Public-facing presentation of the finished project with project summary, dashboard visuals, selected SQL examples, Salesforce screenshots, process diagrams, downloadable resume, and links to supporting materials.

Technology Stack:

• CRM: Salesforce Trailhead Playground, HubSpot concepts and lifecycle design
• Database: PostgreSQL
• SQL Development: DBeaver Community Edition
• Business Intelligence: Microsoft Power BI Desktop
• Spreadsheet Analysis: Microsoft Excel
• Version Control and Portfolio Documentation: GitHub and GitHub Desktop
• Process Mapping: diagrams.net / draw.io
• Documentation and Presentation: Microsoft Word and PowerPoint
• Portfolio Delivery: GitHub Pages or another lightweight personal portfolio website

Success Criteria:

The project will be considered successful if it produces a credible, end-to-end Revenue Operations case study that demonstrates both analytical and operational capability and can be confidently presented to prospective employers.

Specific success criteria include:

• Build a realistic relational CRM dataset and document the underlying data model clearly.
• Identify and quantify meaningful CRM data-quality, routing, pipeline, forecasting, and commercial-process issues.
• Use SQL, Excel, Power BI, and Salesforce in a connected workflow rather than as isolated exercises.
• Develop defensible recommendations that directly address the issues discovered during analysis.
• Create improved lead-routing, lifecycle, pipeline-governance, and Deal Desk processes that are practical and internally consistent.
• Produce a professional Power BI dashboard that enables leadership and sales teams to monitor core revenue and operational KPIs.
• Demonstrate working SQL competency through clearly documented queries that answer real business questions.
• Configure selected Salesforce controls, fields, reports, or workflows that reflect the redesigned operating model.
• Produce documentation, process maps, and an executive presentation that communicate findings clearly to both technical and non-technical stakeholders.
• Publish the finished project through GitHub and a professional portfolio website suitable for inclusion on a resume, LinkedIn profile, and job applications.
• Be able to explain and defend the project’s methodology, findings, tradeoffs, and recommendations in an interview without relying on scripted answers.